## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Projects
| projects-export-2025-12-17 | Projects - projects-export-2025
Dashboard
| Table 1 | Dashboard

## Projects - projects-export-2025
projects-export-2025-12-17
Name | Phase | Cost | Effort | Benefit | Start Date | End Date | NMS Date | Health | Project Days | Daily $ | Daily Effort | Filter Start | Filter End | Filter Days | Filter $ | Filter Effort
SEL 2025 | Delivery | 40000 | 800 | 0 | 2025-01-01 | 2025-12-31 |  | Healthy | 365 | 109.589 | 2.1918 | 2025-04-01 | 2025-06-30 | 91 | 9972.6027 | 199.4521
2025 Existing Program #1 | Delivery | 50000 | 1000 | 0 | 2025-01-01 | 2025-12-31 |  | Healthy | 365 | 136.9863 | 2.7397 | 2025-04-01 | 2025-06-30 | 91 | 12465.7534 | 249.3151
GNB Audit | Delivery | 20000 | 300 | 0 | 2025-01-01 | 2025-06-30 | 2025-24-01 | Caution | 181 | 110.4972 | 1.6575 | 2025-04-01 | 2025-06-30 | 91 | 10055.2486 | 150.8287
Priority Pilot | Delivery | 5000 | 100 | 80 | 2025-03-10 | 2025-05-12 | 2025-15-04 | Healthy | 64 | 78.125 | 1.5625 | 2025-04-01 | 2025-05-12 | 42 | 3281.25 | 65.625
Fundraising25 | Delivery | 20000 | 300 | 100000 | 2025-01-01 | 2025-12-31 |  | Danger | 365 | 54.7945 | 0.82192 | 2025-04-01 | 2025-06-30 | 91 | 4986.3014 | 74.7945
School Support Program 25 | Delivery | 98000 | 2400 | 0 | 2025-01-01 | 2025-12-31 |  | Healthy | 365 | 268.4932 | 6.5753 | 2025-04-01 | 2025-06-30 | 91 | 24432.8767 | 598.3562
RISK1 | Delivery | 5000 | 100 | 0 | 2025-01-01 | 2025-12-31 | 2025-31-03 |  | 365 | 13.6986 | 0.27397 | 2025-04-01 | 2025-06-30 | 91 | 1246.5753 | 24.9315
2025 Admin | Delivery | 40000 | 1000 | 0 | 2025-01-01 | 2025-12-31 |  | Healthy | 365 | 109.589 | 2.7397 | 2025-04-01 | 2025-06-30 | 91 | 9972.6027 | 249.3151
Digital Donor | Delivery | 250000 | 1500 |  | 2024-07-01 | 2025-05-31 |  |  | 335 | 746.2687 | 4.4776 | 2025-04-01 | 2025-05-31 | 61 | 45522.3881 | 273.1343
[13 empty] | Delivery | 740 | 121935.599 | 1885.7524
[9 empty] | 1 | 0 | 0
Seniors Conference 2025 | Discovery | 10000 | 250 | 0 | 2025-04-24 | 2025-07-21 | 2025-21-04 | Healthy | 89 | 112.3596 | 2.809 | 2025-04-24 | 2025-06-30 | 68 | 7640.4494 | 191.0112
Youth Community | Discovery | 60000 | 1800 |  | 2025-03-10 | 2026-06-30 |  |  | 478 | 125.523 | 3.7657 | 2025-04-01 | 2025-06-30 | 91 | 11422.5941 | 342.6778
[13 empty] | Discovery | 159 | 19063.0436 | 533.6891
[9 empty] | 1 | 0 | 0
Close Books for FY24 | Done | 30000 | 200 | 0 | 2025-01-13 | 2025-02-28 |  | Healthy | 47 | 638.2979 | 4.2553 | 2025-04-01 | 2025-02-28 | 0 | 0 | 0
ACGP Funding | Done | 15000 | 250 |  | 2024-10-01 | 2025-04-17 |  | Healthy | 199 | 75.3769 | 1.2563 | 2025-04-01 | 2025-04-17 | 17 | 1281.407 | 21.3568
[13 empty] | Done | 17 | 1281.407 | 21.3568
AGM2025 | Planning | 5000 | 100 | 0 | 2025-08-18 | 2025-09-30 | 2025-24-09 |  | 44 | 113.6364 | 2.2727 | 2025-08-18 | 2025-06-30 | 0 | 0 | 0
New Women's Program | Planning | 30000 | 800 | 0 | 2025-07-01 | 2025-12-31 | 2025-24-06 |  | 184 | 163.0435 | 4.3478 | 2025-07-01 | 2025-06-30 | 0 | 0 | 0
Strat Plan 2030 | Planning | 10000 | 500 | 0 | 2025-06-01 | 2025-08-31 |  |  | 92 | 108.6957 | 5.4348 | 2025-06-01 | 2025-06-30 | 30 | 3260.8696 | 163.0435
Youth Conference 2025 | Planning | 10000 | 250 | 0 | 2025-05-14 | 2025-06-30 | 2025-10-07 |  | 48 | 208.3333 | 5.2083 | 2025-05-14 | 2025-06-30 | 48 | 10000 | 250
[13 empty] | Planning | 78 | 13260.8696 | 413.0435
[15 empty] | 155540.9192 | 2853.8418
Formulas:
Filter Start = IF([Start Date]>'Dashboard'!$B3,[Start Date],'Dashboard'!$B3)
Filter End = IF([End Date]<'Dashboard'!$C3,[End Date],'Dashboard'!$C3)

## Dashboard
Table 1
| Start | End | Number of Days | Default Annual Cost | Calc Budget | $USED | $ left | Default Effort | Effort Used | Calculated BGT Effort | Effort Left | %Cost | %Effort
Dashboard Totals | 2025-04-01 | 2025-06-30 | 91 | 350000 | 87260.274 | 155540.9192 | -68280.6452 | 15000 | 2853.8418 | 3739.726 | 11260.274 | 178.2% | 19.03%
| Inititalives | Cost | Effort
Planning | 2 | 13260.8696 | 413.0435
Discovery | 2 | 19063.0436 | 533.6891
Delivery | 9 | 121935.599 | 1885.7524
Done | 1 | 1281.407 | 21.3568
Total Used |  | 155540.9192 | 2853.8418